## VfMI
|  |  | VALUE FOR MONEY INSTRUMENT (VfMI) FORM | [5 empty] | ROADS FUND BOARD
|  | Agency: |  |  | Original Contract Price:
|  | Project: |  |  | Project Length/ Size
|  | Contract Number: |  |  | Contract Period:
|  | Supervising Engineer: |  |  | Start Date:
|  | Contractor: |  |  | Actual Completion Date:
|  | Audit Date: |  |  | Final Contract Price:
|  |  |  | Evaluation Scale: ® | 1 = Poor; | 2 = Fair; | 3 = Good; | 0 = INA | (INA) = Information not available
NO. |  | INDICATORS/ PARAMETERS/ SUB-PARAMETERS |  |  | EVALUATION SCORE |  |  |  | COMMENTS
[5 empty] | Poor | Fair | Good | INA
Assess all project implementation aspects listed under stages A-E below and rate them as poor, fair or good. If the aspect lacks the required information, its evaluation score should be zero (under "INA" column)
A | Planning, Design and Tender Documentation |  |  |  | 1 | 2 | 3 | 0
[5 empty] | #DIV/0! | #DIV/0! | #DIV/0!
| 1 | Compliance of project planning with requirements of the Performance Agreement, particularly with respect to: |  |  | #DIV/0! | #DIV/0! | #DIV/0!
(1) Assessment of competing alternatives based on updated road inventory and condition survey
(2) Analysis of feasibility based on appropriate road maintenance software (such as HDM 4, DROMAS, or RMMS)
(3) Timely appointment of independent design professional or Consultant
| 2 | Accuracy and completeness of design calculations and technical drawings
| 3 | Accuracy, appropriateness and completeness of technical specifications
| 4 | Overall appropriateness of the design in terms of economy and function (fitness for purpose)
| 5 | Accuracy and completeness of BOQs for the works and their consistency with the drawings and technical specifications
| 6 | Accuracy of the Engineer’s estimates
| 7 | Accuracy and completeness of tender documents
|  |  | → | Count of Score | 0 | 0 | 0 | 0
|  |  | → | Total Count of Score | 0 | 0 | 0 | 0
|  |  | → | Percentage of Count | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | → | Weighting | 0 | 2.5 | 3 | 0
|  | Aggregate Performance: Planning, Design and Tender Documentation | [5 empty] | #DIV/0! | #DIV/0!
B | Procurement Stage |  |  |  | 1 | 2 | 3 | 0 | COMMENTS
| 1 | Appropriateness of the method of procurement [Reg. 149 of GN. No. 446]
[5 empty] | #DIV/0! | #DIV/0! | #DIV/0!
| 2 | Compliance of the procurement process with PPA 2011 and its Regulations [GN. No. 446 of 2013], particularly with respect to: |  |  | #DIV/0! | #DIV/0! | #DIV/0!
(1) Use of standard tender and contract documents [Reg. 184(3) and 287(4) of GN. No. 446]
(2) The tender notice [section 68 (2)]
(3) The selection method [section 64]
(4) Prequalification and shortlisting [section 52]
(5) Time for submitting tenders
(6) Communication of clarification to bidders
[5 empty] | #DIV/0! | #DIV/0! | #DIV/0!
| 3 | Evaluation process and award of contract |  |  | #DIV/0! | #DIV/0! | #DIV/0!
(1) Composition of tender evaluation committee [section 40; Reg. 202(1) and 297(1) of GN. No. 446]
(2) Members of evalaution team signing code of ethics [section 40(6) of PPA 2011]
(3) Evaluation done as per the evaluation criteria contained in the tender dossier or Request forProposal
(4) Minutes of tender board meeting specifying reasons for rejecting a lower tender [Reg. 237(3) of GN. No. 446]
(5) Notification of intention to award the contract [Regulation 231(2) and 231 (3) of GN. No. 446]
(6) Publication of awards [Regulations 20 and 234 of G.N. No. 446]
(7) Quality and comprehensiveness of the tender evaluation report
| 4 | Competitiveness of rates quoted for major items of construction when compared with prevailing market prices
| 5 | Overall competitiveness of the most economic tender compared with prevailing market prices in both private and public sectors
| 6 | Capacity and competence of the selected contractor in relation to project size and complexity
|  |  | → | Count of Score | 0 | 0 | 0 | 0
|  |  | → | Total Count of Score | 0 | 0 | 0 | 0
|  |  | → | Percentage of Count | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | → | Weighting | 0 | 2.5 | 3 | 0
|  | Aggregate Performance: Procurement Stage | [5 empty] | #DIV/0! | #DIV/0!
C | Construction Stage |  |  |  | 1 | 2 | 3 | 0 | COMMENTS
| 1 | Timeliness of site possession
| 2 | Quality of project programme (schedule of work)
| 3 | Adherence to project programme
| 4 | Quality of contractor's site organization and staff
| 5 | Quality of supervising engineer's site staff
| 6 | Quality of quality assurance programme
| 7 | Adherence to quality assurance programme
| 8 | Quality of Environmental Management Plan (EMP)
| 9 | Management of contractual documents, including surety and insurances bonds
[5 empty] | #DIV/0! | #DIV/0! | #DIV/0!
| 10 | Quality and management of project documentation with respect to: |  |  | #DIV/0! | #DIV/0! | #DIV/0!
(1) general correspondence
(2) site instructions
(3) minutes of site meetings
(4) progress reports
(5) works measurement and inspection records
(6) material testing records
(7) interim and final payment certificates
(8) variation orders
(9) claims
| 11 | Assessment (including validity) of variations
| 12 | Assessment (including validity) of claims and related cost overruns
| 13 | Assessment (including validity) of project delays and extensions of time
|  |  | → | Count of Score | 0 | 0 | 0 | 0
|  |  | → | Total Count of Score | 0 | 0 | 0 | 0
|  |  | → | Percentage of Count | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | → | Weighting | 0 | 2.5 | 3 | 0
|  | Aggregate Performance: Construction Supervision and Contract Adminstration | [5 empty] | #DIV/0! | #DIV/0!
D | Project Completion and Closure Stage |  |  |  | 1 | 2 | 3 | 0 | COMMENTS
| 1 | Quality and completeness of as-built-drawings
| 2 | Compilation and Management of snag list
| 3 | Timely issuance of Substantial Completion Certificate, Final Certificate and settlement of Final Account
| 4 | Management of the defects liability period
| 5 | Quality and adequacy of the final project report
| 6 | Compliance of final quantities paid for with those reflected by the actual investment as per as-built-drawings
| 7 | Compliance of project cost as per final account with accepted tender price
| 8 | Compliance of actual project completion time with the contract period
|  |  | → | Count of Score | 0 | 0 | 0 | 0
|  |  | → | Total Count of Score | 0 | 0 | 0 | 0
|  |  | → | Percentage of Count | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | → | Weighting | 0 | 2.5 | 3 | 0
|  | Aggregate Performance: Project Completion and Closure Stage | [5 empty] | #DIV/0! | #DIV/0!
E | Executed Works |  |  |  | 1 | 2 | 3 | 0 | COMMENTS
[5 empty] | #DIV/0! | #DIV/0! | #DIV/0!
| 1 | Based on visual assessment, determine whether the completed works are satisfactory in terms of: |  |  | #DIV/0! | #DIV/0! | #DIV/0!
(1) Overall quality of workmanship
(2) Overall quality of materials used
(3) Overall quality of riding surface
(4) Absence of defects, such as cracks, ruts and localized potholes
(5) Camber and/or super-elevation
(6) Routine maintenance: Grass kept at minimum height: Height less than 50 cm at all time
(7) Routine maintenance: Presence of potholes on paved network: Potholes patched within 48 hours
(8) Routine maintenance: Drainage: Culverts and ditches clear and open
(9) Routine maintenance: No debris and solid waste dumped on road shoulder and drainage system
(10) Routine maintenance: Quality of graded /reshaped unpaved road
(11) Routine maintenance: Quality of pothole patching/ pothole filling for paved/ unpaved road
(12) Routine maintenance: Quality of crack sealing for paved road
(13) Bridges Preventive Mt'ce./ Major repairs: Quality of Bridge Mtce. Works / Major repairs
[5 empty] | #DIV/0! | #DIV/0! | #DIV/0!
| 2 | Based on physical site measurements, determine whether dimensions of the following major items of construction of the completed works comply with the drawings and technical specifications: |  |  | #DIV/0! | #DIV/0! | #DIV/0!
(1) Pavement structure
(2) Road carriageway
(3) Foot paths
(4) Road side drains
(5) Mitre drains
(6) Road signs
| 3 | Based on site measurements, determine whether dimensions of culverts and bridges comply with the technical drawings and specifications
| 4 | Based on sample field tests determine whether the quality of materials used in the pavement structure comply with the technical specifications
| 5 | Based on sample field tests determine whether the quality of materials used in concrete and masonry works comply with the technical specification
| 6 | Assess compliance of site clean-up and restoration of disturbed and/or damaged areas with EM
| 7 | For uncompleted projects, assess compliance of on-going construction activities with safety and EMP requirements
| 8 | Performance Based Contracts: Compliance of Maintenance Services with the required Service Level as per PBC Specifications
| 9 | Performance Based Contracts: Compliance with other Service Quality Levels as per PBC Specifications
|  |  | → | Count of Score | 0 | 0 | 0 | 0
|  |  | → | Total Count of Score | 0 | 0 | 0 | 0
|  |  | → | Percentage of Count | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | → | Weighting | 0 | 2.5 | 3 | 0
| Aggregate Performance: Quality of Works | [6 empty] | #DIV/0! | #DIV/0!
Z | Integrity of Project Implementation |  |  |  | (a) | (b) |  | (c) | SUMMARY OF INTEGRITY EVIDENCE RECORDS
| The Project automatically becomes "NOT Value for Money" if one of the Integrity parameters is assessed to above a value shown in Column (iii) |  |  |  | %ge | Condition |  | Threshold Value
| 1 | Is there any evidence of Inflated quantities in the Bills of Quantities? If so, by what percentage value of the project? |  |  |  | Not VFM if >= |  | 10%
| 2 | Is there any evidence of unjustified Over design? If so, by what percentage value of the project? |  |  |  | Not VFM if >= |  | 25%
| 3 | Is there any evidence of Overpriced Bid? If so, by what percentage value of the project? |  |  |  | Not VFM if >= |  | 30%
| 4 | Are there any Variations with no justification? If so, by what percentage value of the project? |  |  |  | Not VFM if >= |  | 20%
| 5 | Is there substantial unjustified Time overrun? If so, by what percentage value of the approved contract period? |  |  |  | Not VFM if >= |  | 40%
FALSE
| Overall Project Performance: | [6 empty] | #DIV/0! | #DIV/0!
Note on C118: For other types of work, you may substitute these items with relevant ones. Refer to the VfMI User Guide section 6.3.
Note on G14: Instruction: The value to be entered in this column is "1"
Note on G31: Instruction: The value to be entered in this column is "1"
Note on G58: Instruction: The value to be entered in this column is "1"
Note on G87: Instruction: The value to be entered in this column is "1"
Note on G101: Instruction: The value to be entered in this column is "1"
Note on H14: Instruction: The value to be entered in this column is "1"
Note on H31: Instruction: The value to be entered in this column is "1"
Note on H58: Instruction: The value to be entered in this column is "1"
Note on H87: Instruction: The value to be entered in this column is "1"
Note on H101: Instruction: The value to be entered in this column is "1"
Note on I14: Instruction: The value to be entered in this column is "1"
Note on I31: Instruction: The value to be entered in this column is "1"
Note on I58: Instruction: The value to be entered in this column is "1"
Note on I87: Instruction: The value to be entered in this column is "1"
Note on I101: Instruction: The value to be entered in this column is "1"
Note on K11: Do not wrap text even if it gets clipped